## Start here
Change log
Log every change request, its extra hours, its cost at your rate and the decision. Works in Excel and Google Sheets.
Step | What to do | How
1 | Type your hourly rate | On the Change log tab, type your rate for one hour of work in C7, in your own currency. Add the project and client names above it if you like. Until C7 has a number, costs use the EXAMPLE rate of 100.
2 | Delete the EXAMPLE rows | The first five rows show how a filled-in log looks. Delete their contents when you are ready to log your own.
3 | Log each request | One row per request: a short name, the date it came in, who asked, what they asked for and your estimate of the extra hours. Cost works itself out.
4 | Record the decision | Pick Approved, Declined, Not now or Pending. Add the decision date and who signed it off on the client side.
5 | Read the Summary | The Summary tab shows requests, hours and cost per decision, plus the approved total and what still waits for a decision. Share it with the client at each check-in.
Colour key
| Yellow | You type or pick here.
| Grey | Worked out for you. Please do not type here.
| Dark | Column names. Keep the pasted headers as they come from HornetForms.
Good to know
Cost = Impact (hours) x your hourly rate. Change the rate once and every cost updates.
A request with no decision counts as Pending in the Summary.
Use the Notes column for the quote you sent, the new deadline or what you dropped to fit the change in.
Keep one log per project, so the totals stay clear.
This sheet is a planning aid. Your contract decides how changes are priced and agreed.
Example data
The Change log shows five EXAMPLE requests for a website project and uses the EXAMPLE rate of 100 an hour until you type your own rate in C7. Delete the EXAMPLE rows before you start.
Guide: https://hornetforms.com/blog/change-request-process
Made by HornetForms, hornetforms.com

## Change log
Change log
One row per change request. Type your hourly rate once in C7, then the hours for each request. Cost and the Summary fill in on their own.
Project
Client
Your hourly rate
Rate used
# | Request | Date received | Requested by | Description | Impact (hours) | Cost | Decision | Decision date | Signed off by | Notes | Counts as
1 | EXAMPLE: Add a blog section | 2026-12-01 | Dana (client) | Blog list page, a post template and three categories | 14 |  | Approved | 2026-12-03 | Dana | Revised quote sent on 2026-12-02
2 | EXAMPLE: Video in the home page hero | 2026-12-04 | Sam (client) | Swap the hero photo for a short looping video | 6 |  | Not now | 2026-12-05 | Dana | Look again after launch
3 | EXAMPLE: Spanish version of the site | 2026-12-08 | Dana (client) | Eight pages in Spanish, client sends the text | 20 |  | Pending |  |  | Client is checking the budget
4 | EXAMPLE: New button colour | 2026-12-09 | Sam (client) | Green buttons instead of blue across the site | 1 |  | Approved | 2026-12-09 | Dana | Small, fits in the current round
5 | EXAMPLE: Online shop | 2026-12-10 | Lee (client) | Sell 40 products with card payments | 60 |  | Declined | 2026-12-12 | Dana | Outside this project. Quoted as a separate phase
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on C7: Your rate for one hour of work, in your own currency, as a plain number (for example 85). Every Cost uses it. Leave it empty to see the EXAMPLE rate.
Note on C8: Worked out for you: your hourly rate, or the EXAMPLE rate while C7 is empty.
Note on F10: Your estimate of the extra hours this change needs. Use 0 for a swap that adds no time.
Note on G10: Worked out: Impact (hours) x the rate used. Please do not type here.
Note on H10: Approved, Declined, Not now or Pending. A request with no decision counts as Pending.
Note on J10: The person on the client side who said yes or no, as written on the request.

## Summary
Summary: what the changes add up to
Worked out from the Change log tab. Please do not type here.
Decision | Requests | Hours | Cost
All requests
Approved so far
Total | Hours | Cost
Approved changes
Waiting for a decision
A request counts once it has text in the Request column. No decision yet counts as Pending. Cost is in the same currency as your hourly rate.

## Lists
Decisions
Approved
Declined
Not now
Pending
These words feed the Decision dropdown and the Summary. If you rename one, change the same word in the Change log rows that use it.