## Start here
Client offboarding checklist
26 tasks with due dates worked out from the project end date. Works in Excel and Google Sheets.
Step | What to do | How
1 | Type the project end date | On the Checklist tab, fill the yellow boxes at the top: client, project, project lead and the project end date. Until you type an end date, the sheet shows EXAMPLE dates.
2 | Check the due dates | Each due date is the end date plus "Days from end date". A negative number means before the end date. Change the number if a task should move.
3 | Tick Done as you go | Pick Yes in the Done? column and add the date in Done on. Status changes to Done, and late tasks show as Overdue.
4 | Make it yours | Edit any task, or delete one and leave the row blank. Use the blank yellow rows at the bottom for your own tasks: pick a Phase and an Owner, and type the days from the end date.
5 | Read the Summary | The Summary tab shows progress by phase, open and overdue tasks by owner, and the next task due.
Colour key
| Yellow | You type or pick here.
| Grey | Worked out for you. Please do not type here.
| Dark | Column names. Keep the pasted headers as they come from HornetForms.
Good to know
Due dates are worked out from the project end date. Negative days fall before it (-14 is two weeks before).
Weekends are not skipped. If a due date lands on a Saturday or Sunday, edit "Days from end date" for that task.
The tasks are a starting point. Swap in your own, and remove what does not fit your work.
Status uses today's date, so it updates each time you open the file.
The Summary counts a task once it has text in the Task column.
This sheet is a planning aid, not legal advice. Your contract decides what you owe the client at the end.
Example data
The Checklist uses the EXAMPLE end date 2027-01-29 until you type your own in the Project end date box (C8). The names are left empty on purpose. The tasks are a starting point: swap in your own.
Made by HornetForms, hornetforms.com

## Checklist
Client offboarding checklist
Type the project end date once. Due dates and status fill in on their own. Tick Done as you go. Add your own tasks in the blank rows at the bottom.
Client
Project
Project lead
Project end date
End date used
# | Phase | Task | Owner | Days from end date | Due date | Done? | Done on | Notes | Status | Open due date (helper)
1 | Two weeks out | Confirm the end date in writing, and what "done" means for the last deliverables | Account lead | -14
2 | Two weeks out | List every open deliverable and agree what ships before the end date | Project lead | -14
3 | Two weeks out | Read the contract for what you owe at the end: files, source files, licences, notice | Account lead | -12
4 | Two weeks out | List every client account your team can reach, and every place the client can reach in your tools | Project lead | -12
5 | Two weeks out | Tell the client what they will get, in which format and by which date | Account lead | -10
6 | Two weeks out | Book a 30-minute wrap-up call for the last week | Account lead | -10
7 | Two weeks out | Write plain how-to notes: how things work, renewal dates, who to call | Team | -8
8 | Last week | Deliver the final work and ask the client to confirm they have it | Project lead | -5
9 | Last week | Put final files, source files, fonts and licences in one shared folder | Team | -5
10 | Last week | Move ownership of domains, ad accounts, analytics and other client accounts to the client | Project lead | -4
11 | Last week | Hold the wrap-up call: what went well, what is still open, what comes next | Account lead | -3
12 | Last week | Send the final invoice from your billing tool and check that earlier invoices are paid | Finance | -2
13 | Last week | Send the offboarding email with the folder link, the notes and the access list | Account lead | -1
14 | End date | Remove your team from the client's accounts, or ask the client to remove you | Project lead | 0
15 | End date | Remove the client from your project board, chat channels and shared drives | Project lead | 0
16 | End date | Change shared passwords and delete saved client logins from your password manager | Team | 0
17 | End date | Turn off scheduled posts, automations and forms that still run for this project | Team | 0
18 | After the end date | Update your client list with the end date and the main contact | Account lead | 1
19 | After the end date | Send a short feedback form | Account lead | 3
20 | After the end date | Hold an internal review: what to repeat and what to change | Project lead | 7
21 | After the end date | Ask for a testimonial if the feedback was good | Account lead | 7
22 | After the end date | Ask for permission to show the work in your portfolio | Account lead | 10
23 | After the end date | Archive the project files and delete client data you no longer need | Team | 14
24 | After the end date | Add the work to your portfolio, within the limits the client agreed | Team | 21
25 | After the end date | Ask for a case study once the results are in | Account lead | 45
26 | After the end date | Send a friendly check-in and ask if anyone they know needs help | Account lead | 90
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Formulas:
Status = IF([Task]="","",IF([Done?]="Yes","Done",IF([Due date]="","",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+7,"Due this week","Upcoming")))))
Note on C8: The last working day of the project, for example 2027-01-29. Every due date counts from here. Leave it empty to see EXAMPLE dates.
Note on C9: Worked out for you: your end date, or the EXAMPLE date while the end date is empty.
Note on E11: Days after the project end date. Negative means before it (-14 is two weeks before). Weekends are not skipped: change the number to move a task.
Note on F11: Worked out: end date plus Days from end date. Please do not type here.
Note on J11: Done, Overdue (not done and past due), Due this week (due in the next 7 days) or Upcoming.

## Summary
Summary: progress and open tasks
Worked out from the Checklist tab. Please do not type here.
Phase | Tasks | Done | % done
All phases
Owner | Open tasks | Overdue tasks
All owners
Next task due
Last task due
Open means not marked Yes in Done?. Overdue means not done and past its due date. Tasks you add count once they have text in the Task column.

## Lists
Phases | Owners | Done?
Two weeks out | Project lead | Yes
Last week | Account lead | No
End date | Team
After the end date | Finance
Rename a phase or owner here and the dropdowns and Summary follow. Also change the same word in the Checklist rows that use it.