## Start here
Work-order log
Log every maintenance request, who is on it, its status and how long it stays open. Works in Excel and Google Sheets.
Step | What to do | How
1 | Set your target | On the Work-order log tab, type in C5 how many days you aim to take for a repair. The template starts at 7. Open requests older than that turn red.
2 | Delete the EXAMPLE rows | The first six rows show a filled-in log. Delete their contents when you are ready to log your own.
3 | Log each request | One row per problem: the request date, unit or location, what is wrong and the urgency. If requests come from an online form, copy the Submitted at date and the answers from your Google Sheets row or CSV export.
4 | Keep it up to date | Change Status as the job moves (New, Scheduled, In progress, Waiting on parts, Done) and type who is on it under Assigned to. Add the closed date when the job is finished.
5 | Read the Summary | The Summary tab shows open requests by urgency, how many are past your target, the oldest open request and the average days to close.
Color key
| Yellow | You type or pick here.
| Grey | Worked out for you. Please do not type here.
| Dark | Column names. Please keep them as they are.
Good to know
Days open = closed date minus request date. While a job is open, it uses today's date, so the number grows each day until you close the row.
Type dates as dates (2027-06-10). A date typed as text leaves Days open empty.
Use one row per problem, even when one tenant reports two, so each job gets its own closed date.
Emergencies belong on the phone first. Log them here afterwards so the record stays complete.
This sheet is a record-keeping aid, not legal advice. Repair time limits differ by state, city and lease.
Example data
The Work-order log shows six EXAMPLE requests in a small apartment building in October 2026. Delete the EXAMPLE rows before you start.
Guide: https://hornetforms.com/blog/maintenance-request-form
Made by HornetForms, hornetforms.com

## Work-order log
Work-order log
One row per repair request. Type the request date, unit, issue and urgency when it comes in. Update Status and Assigned to as the job moves, and add the closed date when it is done. Days open works itself out.
| Target days to close | 7
# | Request date | Unit or location | Issue | Urgency | Status | Assigned to | Closed date | Days open | Notes | Open? | Days to close | Days open (open rows)
1 | 2026-10-05 | EXAMPLE: Unit 2B | Kitchen sink leaks under the cabinet | Urgent | Done | Marco | 2026-10-06 |  | Replaced the trap seal
2 | 2026-10-09 | EXAMPLE: Unit 4A | Bedroom window will not lock | Urgent | Done | Marco | 2026-10-10 |  | New latch fitted
3 | 2026-10-12 | EXAMPLE: Lobby | Hall light flickers | Routine | Waiting on parts | Priya |  |  | Ballast ordered
4 | 2026-10-19 | EXAMPLE: Unit 1C | No hot water | Urgent | Done | Outside plumber | 2026-10-20 |  | Water heater element replaced
5 | 2026-10-21 | EXAMPLE: Unit 3D | Bathroom fan is noisy | Routine | Scheduled | Priya |  |  | Tenant asked for a call first
6 | 2026-10-26 | EXAMPLE: Unit 2A | Dishwasher will not drain | Routine | New
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Formulas:
Days open = IF(ISNUMBER([Request date]),IF(ISNUMBER([Closed date]),[Closed date]-[Request date],TODAY()-[Request date]),"")
Note on C5: How many days you aim to take for a routine repair, as a whole number. Open requests older than this turn red, and the Summary counts them.
Note on B7: The day the request came in, typed as a date (for example 2027-06-10). From a form, use the Submitted at date.
Note on E7: Emergency, Urgent or Routine. The words come from the Lists tab.
Note on F7: New, Scheduled, In progress, Waiting on parts or Done. A request stays open until Status is Done or it has a closed date.
Note on G7: Who is doing the job: a staff name or an outside company.
Note on I7: Worked out: closed date minus request date, or today minus request date while the job is open. Please do not type here.

## Summary
Summary: what is still open
Worked out from the Work-order log tab. Please do not type here.
Urgency | Open requests | All requests
All urgencies
How long jobs take
Measure | Value
Target days to close (from the log)
Open longer than the target
Oldest open request (days)
Closed requests
Average days to close
A request counts once it has a request date. It stays open until Status is Done or it has a closed date. Days count calendar days, weekends included.

## Lists
Urgency | Status
Emergency | New
Urgent | Scheduled
Routine | In progress
Waiting on parts
Done
These words feed the dropdowns and the Summary. If you rename one, change the same word in the log rows that use it. Keep Done as the last status: the log treats Done as closed.