## Start here
30-60-90 day onboarding plan
An onboarding plan template with due dates worked out from the start date. Works in Excel and Google Sheets.
Step | What to do | How
1 | Type the start date and names | On the Plan tab, fill the yellow boxes at the top: new hire name, role, manager, buddy and start date. Until you type a start date, the sheet shows EXAMPLE dates.
2 | Write the goals | Each phase has a short goal (Get ready, Learn the role, Contribute, Own it). Rewrite them for the role, and change the tasks to match.
3 | Put the check-ins in your calendar | The Check-ins tab works out the 30, 60 and 90-day dates. Add them to your own calendar on day one.
4 | Pick a Status as you go | Not started, In progress, Done or Skipped. Flag shows Overdue for open tasks past their due date and Due this week for the next 7 days.
5 | Read the Summary | The Summary tab shows progress by phase, plus open and overdue tasks by owner.
Color key
| Yellow | You type or pick here.
| Grey | Worked out for you. Please do not type here.
| Dark | Column names. Please keep them as they are.
Good to know
Due dates are worked out from the start date. Due day 0 is day one; negative days fall before it.
Weekends are not skipped. If a due date lands on a Saturday or Sunday, change the Due day for that task.
Type Due day as a plain number. If a cell holds text, the due date stays blank instead of showing an error.
Flag uses today's date, so it updates each time you open the file.
The tasks are a starting point. Swap in your own, and remove what does not fit the role.
This sheet is a planning aid, not legal advice. Check your own rules for paperwork, pay and probation.
Example data
The Plan uses the EXAMPLE start date 2027-05-17 until you type your own in the Start date box (C9). The names and Status column are empty on purpose. The tasks are a starting point: swap in your own.
Made by HornetForms, hornetforms.com

## Plan
30-60-90 day onboarding plan
Type the start date and the names. Due dates and flags fill in on their own. Pick a Status as you go, and add your own tasks in the blank rows at the bottom.
New hire name
Role
Manager
Buddy
Start date
Start date used
# | Phase | Goal | Task | Owner | Due day | Due date | Status | Notes | Flag
1 | Before day one | Get ready | Send the new employee information form with the offer email | HR | -14
2 | Before day one | Get ready | Order the laptop and kit, then set up the work email and accounts | IT | -7
3 | Before day one | Get ready | Write three to five goals for the first 90 days | Manager | -5
4 | Before day one | Get ready | Pick a buddy and plan the first week | Manager | -5
5 | Before day one | Get ready | Put the 30, 60 and 90-day check-ins in your own calendar | Manager | -3
6 | Before day one | Get ready | Send a welcome note with the first-week plan | Manager | -2
7 | Days 1 to 30 | Learn the role | Welcome them in person and walk through this plan | Manager | 0
8 | Days 1 to 30 | Learn the role | Meet the team and the key people outside it | New hire | 5
9 | Days 1 to 30 | Learn the role | Finish one small, real task | New hire | 5
10 | Days 1 to 30 | Learn the role | Start a weekly one-to-one | Manager | 7
11 | Days 1 to 30 | Learn the role | Shadow a teammate on the core work | Buddy | 10
12 | Days 1 to 30 | Learn the role | Finish the training the role needs | New hire | 21
13 | Days 1 to 30 | Learn the role | 30-day check-in: send the check-in form, then talk it through | Manager | 30
14 | Days 31 to 60 | Contribute | Agree on goals for the next 30 days | Manager | 31
15 | Days 31 to 60 | Contribute | Take over one piece of regular work | New hire | 35
16 | Days 31 to 60 | Contribute | Meet one person from another team each week | New hire | 45
17 | Days 31 to 60 | Contribute | Ask two teammates for feedback | Manager | 50
18 | Days 31 to 60 | Contribute | 60-day check-in: review progress against what you expected | Manager | 60
19 | Days 61 to 90 | Own it | Write a development plan together | Manager | 65
20 | Days 61 to 90 | Own it | Lead one small piece of work from start to finish | New hire | 75
21 | Days 61 to 90 | Own it | Ask the new hire to fill in a self evaluation | Manager | 85
22 | Days 61 to 90 | Own it | 90-day check-in: goals met, next goals, feedback on onboarding | Manager | 90
23
24
25
26
27
28
29
30
31
32
33
34
Formulas:
Flag = IF(OR([Task]="",[Due date]="",[Status]="Done",[Status]="Skipped"),"",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+7,"Due this week","")))
Note on C9: The first day of work, for example 2027-05-17. Every due date counts from here. Leave it empty to see EXAMPLE dates.
Note on C10: Worked out for you: your start date, or the EXAMPLE date while Start date is empty.
Note on F12: Days after the start date. 0 is day one. Negative means before day one (-14 is two weeks before). Weekends are not skipped: change the number to move a task.
Note on G12: Worked out: start date plus Due day. Please do not type here.
Note on H12: Not started, In progress, Done or Skipped.
Note on J12: Overdue (not Done or Skipped and past its due date) or Due this week (due in the next 7 days). Blank otherwise.

## Check-ins
Check-ins at 30, 60 and 90 days
Dates come from the start date on the Plan tab. Put each one in your own calendar on day one, then type the date you held it.
Check-in | Day | Date | Held on | Talk about | Notes
30-day check-in | 30 |  |  | How is it going so far? Are the goals clear? What do you need more of?
60-day check-in | 60 |  |  | Review progress against what you expected. Agree on the goals for the next 30 days.
90-day check-in | 90 |  |  | Goals met, goals for the next six months, and feedback on onboarding.
Held
The check-in form in the post asks the same questions each time, plus one feedback question at day 90. Send the link yourself a few days before each date.

## Summary
Summary: progress by phase and owner
Worked out from the Plan tab. Please do not type here.
Phase | Tasks | Done | Skipped | Open | Overdue | % done
All phases
Owner | Open tasks | Overdue tasks
All owners
Open means not Done and not Skipped. % done leaves Skipped tasks out. Tasks you add count once they have text in the Task column.

## Lists
Phases | Owners | Status
Before day one | Manager | Not started
Days 1 to 30 | New hire | In progress
Days 31 to 60 | HR | Done
Days 61 to 90 | IT | Skipped
Buddy
Rename a phase or owner here and the dropdowns and Summary follow. Also change the same word in the Plan rows that use it.